## Suggested Timeline
Appendix 4 - Suggested SLT Timeline
Point
Date | Activity
3/1/2015 - 6/1/2015 | Run EIS Facility Configuration reports and compare to your local system to insure IDs still match and to identify new facilities, units, processes, release points that need to be created in EIS.
Develop facility inventory submission to update EIS with changes to status, new facilities, units, processes and release points.
If using staging tables; run embedded queries to check for widows and orphans prior to conversion
Submit facility inventory data to the EIS QA Environment. Check Potential Duplicates section of feedback report and resolve any real duplicates as opposed to actual new facilities that need to be added. Revise or add facility IDs in EIS as needed to allow EIS to recognize the correct facility when you submit to Production.
Check number of facility, unit, process and release point records received on the Statistics tab of feedback report against number of records submitted.
Resolve all critical errors in facility feedback report
Submit facility inventory data to the EIS Production Environment. Note that you only need to submit data for items that have changed between your system and EIS. Existing facilities and units and release points do not need to have locations, unit types, release parameters, etc reported to EIS each year if they are already in EIS and acceptable. In particular, if your system does not contain information on unit type or other data fields in EIS, do not include those fields in your submittal with "unclassified/miscellaneous" for existing facilities.
Check Potential Duplicates section of EIS and resolve any issues by contacting EIAG to add or merge facilities.
6/1/2015 - 10/1/2015 | Download landing/takeoff data for review from 2014 website
Download expected pollutants list from 2014 website
Develop emissions (point) inventory for submission to EIS
Submit point inventory to the EIS QA Environment
Check number of reporting period and emission records received on the Statistics tab of the feedback report against the number of records submitted.
Resolve all critical errors in point feedback report
Review emission range warnings for possible outliers or incorrect entry
Submit data to the EIS Production Environment
10/1/2015-12/1/2015 | Run suggested QA reports in Appendix 4
Review expected pollutants list against data submitted.
Run completetion report to verify everything has been submitted
12/1/2015-1/15/2016 | Address any last minute adjustments
Nonpoint
Date | Activity
1/1/2015-6/1/2015 | Download Nonpoint Survey from the 2014 Website
Review list of sectors for which EPA will develop estimates
Determine which sectors will be submitted to EIS and which sectors you will accept EPA estimates.
For the sectors where you will be submitting data, determine when activity data will be available in order to determine when your estimates should be submitted to EIS. (Section 5.4.2)
Submit Nonpoint survey to EPA by 6/1/2016
6/1/2015-10/1/2015 | Download rail/commercial marine vessel shapefile fractions from 2014 website
Download expected pollutant list from 2014 website
Develop Nonpoint inventories for sector where activity data is available or you do not expect to have activity data by 2/2017. Section 5.4.2)
Check that activity data for all agricultural fires as been completed (Section 7.2)
Submit data to the EIS QA Environment
Check number of emisison process, reporting period and emission records received on the Statistics tab of feedback report against the number of records submitted. The statistics should equal the d
Resolve all critical erors in feedback report
Review emission range warnings for possible outliers or incorrect entry
Submit data to the EIS Production Environment
10/1/2015-11/1/2015 | Run suggested QA reports listed in Appendix 4
Run completetion report to verify everything has been submitted
11/1/2015-1/15/2016 | Address any last minute adjustments
Mobile
Date | Activity
6/1/2015-12/1/2015 | Download onroad and nonroad inputs from the EIS Gateway
Adjust inputs (e.g., VMT, inspection maintenance, etc)
Package submission according to instructions posted on 2014 website
Run QA Tool posted on 2014 website
Submit to EIS QA Production
Resolve all critical erors in feedback report
Submit to EIS Production Environment
12/1/2015-1/15/2016 | Address any last minute adjustments
Events
Date | Activity
2015-06-01 | Download Smartfire preliminary results from 2014 website.
6/1/2015-9/1/2015 | Review and submit activity updates using posted template on 2014 website
10/1/2015 - 11/1/2015 | Review of new Smartfire run with updated activity data.

## Suggested QA
Appendix 1 - Suggested QA Reports
Note: All reports should be run the day following a submission. EIS must do a nightly refresh before your data is available in the reports
Point
Type | Report Type | Dataset | Pollutants | Geographic Region | Checks
Type | Report Type | Dataset | Pollutants | Geographic Region | Checks
Emisison Summary - By Geography | State or County Level | Your Agency Dataset | All Active Pollutants | Your state or county | Check that state/pollutant combinaton totals equal the state/pollutant combinations that you intended to submit to EIS. This will assure that a) all of your emissions data successfully made it into the xml file, and b) all of the xml data was accepted by EIS. If there are significant differences, run a facility or unit or process level EIS report and compare to your system's sums to identify where the differences are coming from.
Comparison - Facility | Facility Level | Your current Agency Dataset; 2011 Agency Dataset; 2011 v2 NEI | All Active Pollutants | Your state or county | Compare your 2014 submitted and accepted emissions to either your 2011 submission or to the 2011 NEI. Look for large differences which might indicate reporting errors. Check that all pollutants reported in 2011 have been reported in 2014.
Emisison Summary - By Facility | Facility Level | Your Agency Dataset | All Active Pollutants | Your state or county | Sort for Top 25 facilities for each pollutant reported. Do they make sense?
Nonpoint
Type | Report Type | Dataset | Pollutants | Geographic Region | Checks
Emission Summary - By Geography | SLT by Sector | Your Agency Dataset | All Active | Your state, county or Tribe | Check that the state (county or Tribe)/sector/pollutant in EIS are the same as the file you submitted. If there are differences, run the same report at the SCC level until you can highlight where the differences are coming from.
Comparison | Sector | Your current Agency Dataset; 2011 Agency Dataset | All Active | Your state, county or Tribe | Compare your 2014 submission to your 2011 submission. Check that all pollutants and sectors reported in 2011 have been reported in 2014. If there ae differences, run the same report at the SCC level to determine the location of the erroneous or missing data.