## DE FY14 Q1
Department of Mines, Minerals and Energy Division of Energy Service Results and Performance Measures FY14 Q1 Report September 30, 2013
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Revolving Loan Fund
1.01.00 | 1.01.02
To implement and manage energy efficiency and renewable energy programs through June 30, 2014. | DE Staff will administer Revolving Loan Funds to finance Energy Efficiency and Renewable Energy Projects. |  | Energize Virginia, a revolving loan fund, was capitalized with $10.5 million in federal Recovery Act funds. Six loans were made between April and July 2012 to competitively selected state and local government EE and RE project proposals. The Town of South Boston determined in June 2013 that its proposal to generate electricity from landfill gas was not feasible. Therefore, the Town returned the principal amount of the loan plus interest. Four of the six loans are in the process of repaying or paid in full. One loan's first payment is due in January 2014. One loan is a balloon note due July 30, 2019.
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
ARRA
1.01.00 Continued | 1.01.05
To implement and manage energy efficiency and renewable energy programs through June 30, 2014. | DE staff will continue to collect and report data required to comply with reporting requirements for our programs through June 30, 2014. |  | All Recovery Act funded programs and projects have expended federal grant funds on time. The Southeast Propane Autogas Development Project, a four-year project, is on track to close on the December 6, 2013 federal deadline and expend 100 percent of federal funds by the end of the 90-day administrative grant close-out and final reporting period.
Core Program Functions
1.02.00 | 1.02.05
To ensure continuation of core program functions with less reliance on federal funding through June 30, 2014. | DE staff will report on program status and needs to the DMME Strategic Team by June 30, 2014. |  | Expected severe cuts in annual SEP funds, which were impetus for this strategy, did not materialize. A regional building energy retrofit program is an example of DE adapting post-Recovery Act to support a core program function. Funds invested in a loan program were reprogrammed in an RFP to help three regional "home performance" programs to transition to market-based sustainability. The 2-year goal for home retrofits was 700; 356 were completed by the end of the project on September 29, 2013.
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Alternative Fuel Vehicles
1.04.00 | 1.04.10
To improve our customers’ ability to make informed energy choices to support economic development, create jobs, and enhance the environment through June 30, 2014. | DE staff will track and report performance of programs such as biofuels production, increase in the number of alternative fuel vehicles in participating fleets, and installed renewable energy capacity. |  | The most current statistics depict that 28% (16,630 vehicles) of the vehicles in the fleets that report metrics to Virginia Clean Cities are alternative fuel vehicles (AFVs). AFVs comprised 26% (15,204 vehicles) of the total vehicles in those fleets in the six-month reporting period that ended December 31, 2012.
1.04.00 Continued | 1.04.10 Continued
To improve our customers’ ability to make informed energy choices to support economic development, create jobs, and enhance the environment through June 30, 2014. | DE staff will track and report performance of programs such as biofuels production, increase in the number of alternative fuel vehicles in participating fleets, and installed renewable energy capacity. |  | Virginia has lost 2 biodiesel stations and 9 LPG stations. Virginia has also lost a hydrogen station that had been located at a National Park in Petersburg. Station growth was experienced with the additions of 3 E85, 1 CNG, and 12 electric vehicle charging stations. There are now 34 biodiesel, 18 CNG, 22 E85, 1 hydrogen, 61 LPG propane, 2 LNG, and 152 electric vehicle charging stations in the Commonwealth. As of July 2013, Virginia has a total of 290 fueling stations, up from 286 sites in 2012. This is a gain of 4 stations.
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Net Metering
1.04.00 Continued | 1.04.10 Continued
To improve our customers’ ability to make informed energy choices to support economic development, create jobs, and enhance the environment through June 30, 2014. | DE staff will track and report performance of programs such as biofuels production, increase in the number of alternative fuel vehicles in participating fleets, and installed renewable energy capacity. | Net Metering | Solar and wind power installations tracked via SCC Net Metering Interconnection Notifications and non-net metered systems as we become aware of them. For example, the total amount of net metered solar for Q1-2014 is 9.5 megawatts, whereas the graph to the left includes a 2 megawatt naval installation, and two systems at VA facilities totaling 3.5 megawatts that are NOT considered as net metered systems. The table below details current net metered installations.
Net Metering Details
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Energy Procurement Program
2.01.00 | 2.01.07
To implement and manage a multi-fuel energy procurement program, incorporating renewables through June 30, 2014. | VEMP staff will measure the total dollar value of energy contracts and illustrate the benefits on the DE webpage. |  | Budget and supply certainty are goals of the energy and fuel procurement programs. Electricity purchases from IOUs are negotiated at a low rate relative to similar commercial account classes. The 2013 decline in total value is a result of a change in the source of data from financial reports to fuel vendor reports.
Energy Consumption
2.02.00 | 2.02.06
To reduce the growth of energy consumption by participating government entities by June 30, 2014. | VEMP staff will track and report reductions in energy consumption by participating state agencies. |  | Annual ESPC values, guaranteed and actual “savings” (avoided utility and operational costs) in recent years for state agencies using the state contract for ESPC. These numbers are updated at the end of each fiscal year.
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Demand Response
2.03.00 | 2.03.05
To enable public bodies to reduce peak electrical demand through participation in the Demand Response programs through June 30, 2014. | VEMP staff will track and report the number of facilities in the program, load reductions and revenue generated. |  | There are 71 government facilities enrolled in demand response programs, up 5 facilities from the previous year. This information is updated at the end of the fiscal year.
Training Work Group (TWG)
3.01.00 | 3.01.06
To enable all DE employees to excel in meeting the objectives established in their Employee Work Profile by June 30, 2014. | DE’s Training Work Group (TWG) will survey staff by September 30, 2013 to determine training needs, recommend action to address these needs by December 31, 2013, implement these actions by January 31, 2014, and evaluate their effectiveness in a follow-up survey by June 30, 2014. |  | DE's Training Work Group (TWG) has surveyed the DE Staff and are in the process of developing recommendations to address these needs on or before December 31, 2013.
OBJECTIVE | MEASUREMENTS | RESULTS | EXPLANATION
Training Work Group (TWG)
3.01.00 Continued | 3.01.06
To enable all DE employees to excel in meeting the objectives established in their Employee Work Profile by June 30, 2014. | DE’s Training Work Group (TWG) will survey staff by September 30, 2014 to determine training needs, recommend action to address these needs by December 31, 2013, implement these actions by January 31, 2014, and evaluate their effectiveness in a follow-up survey by June 30, 2014. |  | DE's Training Work Group has surveyed DE Staff to determine their training needs. This is one of the questions contained in the survey. The TWG has set up a folder on DE Shares that contains a spreadsheet with a tab for each employee to log their training taken. The Administrator then uploads their training courses to DMME University. In addition, there is a tab for 'Optional Training' that lists available training that an employee can take. The TWG researches courses that are applicable to the staff's needs and lists them on the Optional Training tab. In addition, when new training courses are added to the list, an email notifying DE staff of a new training opportunity is sent by the TWG.
Surveys
3.02.00 | 3.02.07
To ensure that resources are used efficiently and programs are managed effectively and in a manner consistent with applicable state, federal and agency requirements through June 30, 2014. | DE staff will survey its customers using automated web tools to determine their satisfaction with services provided with a 90% meets or exceeds their expectations rating. |  | SEP staff conducts a customer satisfaction survey that is on-going. Every DE staff member has a request to complete a survey underneath their email signature line. Results show that 87.5% of the customers are satisfied with the services received from DE personnel. Although 12.5% were not satisfied, this depicts only one customer response.

## RLF 1.01.03
RLF Name | Total Loan Amount (Principle) | Total Interest - Life of Loan | Total of Principle + Interest Due | Principle Paid | Interest Paid | Total Paid
Buchanan County Schools | 2332000 | 213565.32 | 2545565.32 | 0 | 0 | 0
Buchanan Cty. Schools | 2332000 | 213565.32 | 2545565.32 | 0 | 0 | 0
Dept. of Corrections | 2500000 | 241901.44 | 2741901.44 | 37766.79 | 47839.51 | 85606.3
Dept. of Corrections | 2500000 | 241901.44 | 2741901.44 | 37766.79 | 47839.51 | 85606.3
Dept. of General Services | 4102000 | $- | 4102000 | 0 | 0 | 0
Dept. of General Svcs. | 4102000 | 0 | 4102000 | 0 | 0 | 0
Pulaski County | 420000 | 29964.2 | 449964.2 | 14060.15 | 1995 | 16055.15
Pulaski County |  |  |  | 14126.94 | 1928.21 | 16055.15
Pulaski County |  |  |  | 14194.04 | 1861.11 | 16055.15
Pulaski County |  |  |  | 14261.46 | 1793.69 | 16055.15
Pulaski County |  |  |  | 14329.2 | 1725.95 | 16055.15
Pulaski County |  |  |  | 14397.27 | 1657.88 | 16055.15
Pulaski County | 420000 | 29964.2 | 449964.2 | 85369.06 | 10961.84 | 96330.9
Southwest VA Regional Jail | 542000 | 44060.99 | 586060.99 | 15722.97 | 2574.5 | 18297.47
Southwest VA Regional Jail |  |  |  | 15797.66 | 2499.82 | 18297.48
Southwest VA Regional Jail |  |  |  | 15872.69 | 2424.78 | 18297.47
Southwest VA Regional Jail |  |  |  | 15948.09 | 2349.38 | 18297.47
Southwest VA Regional Jail |  |  |  | 16023.84 | 2273.63 | 18297.47
Southwest VA Regional Jail |  |  |  | 16099.95 | 2197.52 | 18297.47
SWVA Regional Jail | 542000 | 44060.99 | 586060.99 | 95465.2 | 14319.63 | 109784.83
Town of South Boston | 356000 | 29026.71 | 385026.71 | 356000 | 6746 | 362746
Town of So. Boston | 356000 | 29026.71 | 385026.71 | 356000 | 6746 | 362746
RLF Name | Loan Amount | Principle Paid | Interest Paid | Total Paid
Buchanan County Schools |  | 0 | 0 | 0
Buchanan Cty. Schools $2,332,000 | 2332000 | 0 | 0 | 0
Dept. of Corrections |  | 37766.79 | 47839.51 | 85606.3
Dept. of Corrections $2,500,000 | 2500000 | 37766.79 | 47839.51 | 85606.3
Dept. of General Services |  | 0 | 0 | 0
Dept. of General Svcs. $4,102,000 | 4102000 | 0 | 0 | 0
Pulaski County |  | 14060.15 | 1995 | 16055.15
Pulaski County |  | 14126.94 | 1928.21 | 16055.15
Pulaski County |  | 14194.04 | 1861.11 | 16055.15
Pulaski County |  | 14261.46 | 1793.69 | 16055.15
Pulaski County |  | 14329.2 | 1725.95 | 16055.15
Pulaski County |  | 14397.27 | 1657.88 | 16055.15
Pulaski County $420,000 | 420000 | 85369.06 | 10961.84 | 96330.9
Southwest VA Regional Jail |  | 15722.97 | 2574.5 | 18297.47
Southwest VA Regional Jail |  | 15797.66 | 2499.82 | 18297.48
Southwest VA Regional Jail |  | 15872.69 | 2424.78 | 18297.47
Southwest VA Regional Jail |  | 15948.09 | 2349.38 | 18297.47
Southwest VA Regional Jail |  | 16023.84 | 2273.63 | 18297.47
Southwest VA Regional Jail |  | 16099.95 | 2197.52 | 18297.47
SWVA Regional Jail $542,000 | 542000 | 95465.2 | 14319.63 | 109784.83
Town of South Boston |  | 356000 | 6746 | 362746
Town of So. Boston $356,000 | 356000 | 356000 | 6746 | 362746

## ARRA 1.01.06
Sources | Allocation | Spent | Remaining
SEP | 70001000 | 70001000 | 0
EECBG | 16145300 | 16145300 | 0
Propane | 8605100 | 8351547 | 253553
Appliance | 7454000 | 7454000 | 0
EA | 915000 | 915000 | 0
Total | 103120400 | 102866847 | 253553

## Building Retrofits 1.02.06
Quarter | Number of Projects
FY12 Q4 | 44
FY13 Q1 | 34
FY13 Q2 | 56
FY13 Q3 | 91
FY13 Q4 | 22
FY14 Q1 | 109
Total | 356

## AFV & Sites 1.04.10
Virginia Alternative Fuel Stations | Biodiesel | CNG | E85 | Hydrogen | LNG | LPG Propane | Electric | Total Alt Fuel Stations
2008 | 40 | 12 | 4 | 1 |  | 26 |  | 83
2009 | 38 | 11 | 8 | 1 |  | 27 | 1 | 86
2010 | 44 | 14 | 11 | 1 |  | 49 | 4 | 123
2011 | 48 | 12 | 15 | 1 |  | 66 | 47 | 189
2012 | 36 | 17 | 19 | 2 | 2 | 70 | 140 | 286
mid 2013 | 34 | 18 | 22 | 1 | 2 | 61 | 152 | 290
Total AFV Stations | 240 | 84 | 79 | 7 |  | 299 | 344 | 1057 |  | 37
Virginia Alternative Fuel Vehicles | CNG | E85 | HEV | Elec | Biod | LPG | Total AFV | Total Vehicles | % AFV
January - June 2013 | 1386 | 8522 | 1690 | 225 | 4357 | 450 | 16630 | 59498 | 27.95%
July - Dec. 2012 | 1301 | 7058 | 1665 | 130 | 4620 | 430 | 15204 | 58184 | 26.13%
January - June 2012 | 1269 | 6843 | 2463 | 128 | 4226 | 426 | 14399 | 56792 | 25.35%
August - Dec. 2011 | 711 | 5811 | 790 | 122 | 4855 | 389 | 12678 | 53273 | 23.8%
Note on H18: jzc: Al changed to 14399 from 15355 because the lower number appeared elsewhere in the data. Alleyn confirmed that 14399 is the correct value.

## Energy Contracts 2.01.07
FY2010 | FY2011 | FY2012 | FY2013
285988414 | 300287835 | 315302226 | 178015519
FY2013
|  |  |  | 144188989 | Dominion
|  |  |  | 11736828 | Appalachian
|  |  |  | 10551000 | Natural Gas
|  |  |  | 11538702 | Heating Oil
|  |  |  | 178015519 | Total
These numbers are only updated at the end of each fiscal year.

## Performance Contracting 2.02.06
Contract $ FY09 | 47510355
Guaranteed $ Savings FY09 | 17677934
Actual $ Savings FY09 | 19037478
Contract $ FY10 | 52229197
Guaranteed $ Savings FY10 | 19605084
Actual $ Savings FY10 | 22306170
Contract $ FY11 | 72559031
Guaranteed $ Savings FY11 | 23876275
Actual $ Savings FY11 | 25862483
Contract $ FY12 | 48935133
Guaranteed $ Savings FY12 | 25391774
Actual $ Savings FY12 | 27667675
Contract $ FY13 | 17634258
Guaranteed $ Savings FY13 | 29592236
Actual $ Savings FY13 | 30234365
These numbers are only updated at the end of each fiscal year.
Contract $ Total FY01-FY07 | 145570918
Guaranteed $ Savings FY01-FY07 | 6349038
Cumulative $ Savings FY01-FY07 | 8694194
Contract $ FY08 | 15262642
Guaranteed $ Savings FY08 | 7206165
Actual $ Savings FY08 | 7358839
Contract $ FY09 | 47510355
Guaranteed $ Savings FY09 | 17677934
Actual $ Savings FY09 | 19037478
Contract $ FY10 | 52229197
Guaranteed $ Savings FY10 | 19605084
Actual $ Savings FY10 | 22306170
Contract $ FY11 | 72559031
Guaranteed $ Savings FY11 | 23876275
Actual $ Savings FY11 | 25862483
Contract $ FY12 | 48935133
Guaranteed $ Savings FY12 | 25391774
Actual $ Savings FY12 | 27667675
Contract $ FY13 | 17634258
Guaranteed $ Savings FY13 | 29592236
Actual $ Savings FY13 | 30234365
Contract $ Total FY01-FY13 | 399701534
Guaranteed $ Savings FY01-FY13 | 129698506
Cumulative $ Savings FY01-FY13 | 141161204

## Demand Response 2.03.04
Year | Actual Payments
FY 2012 | 1235177.94
FY 2013 | 1574090.16
new FY2013 | 1378633
These numbers are only updated at the end of each fiscal year.

## TWG 3.01.04
TWG Milestones | Completed
Develop Training Survey for DE Personnel | 100%
Survey DE Personnel | 100%
Research Training/Educational Needs | 25%
Provide List of Training Opportunities to DE Personnel | 2%
Make entries in to the DMME University System | 2%
Follow-up survey to DE Personnel to evaluate TWG's effectiveness by June 30, 2014. | 2%
This is a copy from Survey Monkey. The data was
compiled within Survey Monkey.
TWG Milestones

## Surveys 3.02.08
Do you plan to use any of the "Optional Training" information provided in the "Training" file folder on DE Shares folder to find other training of specific programmatic interest to you? | Do you plan to use any of the "Optional Training" information provided in the "Training" file folder on DE Shares folder to find other training of specific programmatic interest to you? | Do you plan to use any of the "Optional Training" information provided in the "Training" file folder on DE Shares folder to find other training of specific programmatic interest to you? | Do you plan to use any of the "Optional Training" information provided in the "Training" file folder on DE Shares folder to find other training of specific programmatic interest to you?
Answer Options | Answer Options | Response Percent | Response Count
Yes | Yes | 88.9% | 8
No | No | 11.1% | 1
Comments | Comments | 0 | 0
answered question | answered question | 9 | 9
skipped question | skipped question | 0 | 0
Customer Service Survey | Customer Service Survey | Customer Service Survey | Customer Service Survey
How helpful were the customer representatives at DMME? | How helpful were the customer representatives at DMME? | How helpful were the customer representatives at DMME? | How helpful were the customer representatives at DMME?
Answer Options | Answer Options | Response Percent | Response Count
Extremely helpful | Extremely helpful | 75% | 6
Very helpful | Very helpful | 12.5% | 1
Moderately helpful | Moderately helpful | 0% | 0
Slightly helpful | Slightly helpful | 0% | 0
Not at all helpful | Not at all helpful | 12.5% | 1
answered question | answered question | 8 | 8
skipped question | skipped question | 0 | 0